## Project tracker
MACT Machine Guarding Tracker
Complete or Open | Equipment/Area | What is to be done | Hold ups | Estimated finish | Actual finish | Notes
open | Tam Furnace Furnace Entrance | Extend down or replace existing side guards | Going to have meeting with maintenance to deicide wether to get quote one doing the whole line or fixing what we already have | 2024-06-01 | 2024-05-03
open | Tam Quench Where glass walls meet yellow quench guards | Replace bent gaurding | Same as above | 2024-06-01 | 2024-04-29
open | Tam Offload Right side of offload conveyor | Extend down or replace existing side guards | Same as above | 2024-06-01 | 2024-05-03
open | Tam Blower Room Main blower fan | Cover Hydraulic lifting arm | Waiting on Carolina Star evaluation | 2024-07-01 | N/A
Complete | Glasstech Breakout First part of O"seam conveyor | Replace roller wheel |  | N/A | 2024-03-28
open | Glasstech Furnace Furnace entrance | Add a barrier/ guard at furnace entrance |  | 2024-05-01 | 2024-05-07
open | Glasstech Quench Both sides of the quench | Cover Hydraulic Shafts | Waiting on Carolina Star evaluation | 2024-07-01 | N/A
open | Glasstech Blower Room | Cover all lifting arms or lock up and only allow authorized employees in blower room | Waiting on Carolina Star evaluation | 2024-05-01 | N/A